## Current Jobs
v14 16/1/19
DCC- Derbyshire County Council; AVBC - Amber Valley Borough Council
Date Raised | Item | Problem | Location | Allocated to | Parish Councillor Lead | Progress / Outcome
2017-10-23 | 1 | Derbyshire stone wall | Coach Rd | DCC/Futures Housing | Pete Clerk | DCC owned but don't see as a priority
2017-10-25 | 5 | flaked paintwork on safety railings | Cinder Bank | DCC | Clerk (raised by Pete Clark) | JB at DCC confirmed 27/11 Contractor has been assigned this task chased up 17/3/19
2017-10-25 | 7 | BWB No Tipping Sign | King William Bridge Listed Stone bridge | Canal & Rivers Trust | Pete Clark | Have written & had acknowledgement - Waiting for CRT response
2017-10-25 | 8 | Graffiti Monkey Bridge | Codonr Park Sidings | Network Rail | Cllr P Clark | In hand. Added to DCC clean up works, Clerk has got paint/permission from Network Rail. Chased up Seamus 2/9
2017-10-25 | 9 | Graffiti & Trees MRB bridge | B6016 | Midland Rail Alan Calladine | Cllr P Clark | On going plan following MRB site visit Nov 2017
2017-12-07 | 12 | Potholes, surface Deterioration | Parkside Drive | DCC | Cllr P Clark | Work is scheduled. F367834 (07/12/17) DCC hired extra operatives, Have repeated request Mar 2019 online with photos
2017-12-31 | 15 | Historic canal slagstone wall deterioration | Parkside Drive | Prvate owner Stephen Millar (Builder, lives Belper) | Cllr P Clark | Owner (Stephen Millar) has agreed to sort. Clerk wrote to Mr Millar 2/9/18; reminder sent 17/3/19 (Note owner is rarely there and the site in poor condition - think again)
2018-01-10 | 20 | Dirty Street signs | Various Locations | AVBC | Parish Clerk (raised by P Clark) | reported 29/12 F381447. Chased 26/4/18 , The CP signs are done. Not sure if there are any others requested. Job done?
2018-01-10 | 21 | Tree growing out of Network Rail bridge |  | NR | Cllr P Clark | Cllr Clark confirmed has this in hand
2018-01-10 | 22 | Rusty green pipe rotten timber support over canal & public footpath | over adelaide walk | one side gas, other is water | Cllr P Clark | To contact gas and water companies
2018-09-10 | 26 | Vintage lamp posts | Station Road |  | I&CP Volunteers (raised by P Clark) | agreed at Council meeting to accept offer of painting
2017-10-25 | 3 | Shabby AVBC Market St sign | Post Office | AVBC | Parish Clerk (raised by P Clark) | AVBC confirmed sign has been cleaned; request to move rotten posts 17/3/19
2019-03-21 | 30 | Footbridge - shabby green paintwork last done 20 years ago. Also Graffitii | over DCC owned Pinxton Canal rear Casson Street | DCC | Cllr P Clark
2019-05-22
2019-09-08 | 34 | Substation graffitti | King William/Albert stree | WPD | Cllr P Clark | reported
Note on G4: Resident email 2/10/17 = I am really concerned with the state of The Coach Road Ironville end. The canal wall is in a serious state of repair it is extremely dangerous with areas of wall missing. The bad weather with snow and ice is fast approaching and it is a sheer drop down an extensive slope straight into the canal it is an accident with catastrophic consequences waiting to happen. There is also lots of debris in the roadside. Is there something that can be done urgently regarding this I have seen so many near misses including myself.

## Completed Jobs
Date Raised | Item | Problem | Location | Allocated to | Parish Councillor Lead | Progress / Outcome
2017-10-25 | 2 | Bike Tyre obscuring School sign | Cinder Bank | DCC | Cllr P Clark | F371681 (10/12/17) REMOVED
2017-10-25 | 6 | Broken bus sign | Cinder Bank | DCC | Parish Clerk | Fixed 4/1/2018
2017-11-20 | 10 | Christmas Lights | Cinder Bank | Parish Clerk | Parish Clerk | On Clerk's work plan
2017-11-20 | 11 | Lack Defibrilator | Phone kiosk | British Telecom | Parish Clerk | Bid submitted to BHF 27/12/17. Awards for All application to be done next
2018-01-10 | 17 | Graffiti on brick wall |  | DCC | Parish Clerk to add to clean up app (DCC) | duplicate of item 9
2018-03-01 | 23 | Road Sweeping | in areas highlighted | AVBC | Cllr P Clark | AVBC to areas highlighted by councillors to job list
2018-01-10 | 19 | Pot Holes |  | DCC | Parish Clerk | Extra operatives recruited by DCC
2018-09-26 | 25 | glass and litter | king William centre waterside/steps up to cinderbank | AVBC/DPC | Parish Clerk | Warden cleared litter; glass reported to DS at AVBC
2018-09-02 | 24 | Overhanging Hedges Coach Road | Coach Road | DCC | Parish Clerk | The Highway Inspector has advised that following an inspection he did not identify any issues with overgrown vegetation on the Coach Road, Ironville, however we will continue to monitor the condition as part of our routine highway inspections
2018-01-10 | 20 | Dirty Street signs | Various Locations | AVBC | Parish Clerk | reported 29/12 F381447. Chased 26/4/18 ,
2018-11-28 | 27 | The pedestrian barrier broken off and is leaning against a tree | Cinder Bank | DCC | Cllr P Smith | F521600 Job completed
2018-01-02 | 16 | Fly Tipping - 2 seater settee | path behind church | DCC | Cllr Smith | Cllr Smith and Countryside DCC team liaising
2017-12-31 | 14 | Historic canal slagstone wall deterioration | behind Waterside | Futures Homes | Parish Clerk | assests surveyor to assses, will be repointed if necessary
2018-03-02 | 23 | Request to demolish 12 garages | back of Victoria Street/Elizabeth Park Ironville. | Future Housing | Parish Clerk | some occupied; FH no plans to demolish
2019-03-21 | 31 | Brick Wall graffiti "ANARCHY" by toddlers playground | New road, Codnor Park | WPD | Parish Clerk | Cleared 30/4/19
2018-03-21 | 32 | fallen trees near Monkey Bridge | Monkey Bridge | DCC Highways | Cllr P Smith | Cleared
2019-03-17 | 29 | Dangerous Parking | Bottom of Riddings Hill/corner of Victoria Street | Police | Cllr J Bates | reported to Riddings and Somercotes SNT via online form 17/3/19. Nothing else IPC can do
| 27 | The pedestrian barrier broken off and is leaning against a tree | Cinder Bank | DCC | Cllr P Smith | F521600 Job completed
| 28 | Debris in garden an eyesore and fires | 14 Queen Street | Futures Housing | Cllr J Bates | reported to Futures Housing 17/3/19
| 33 | Substation | Behind Elizabeth Park | WPD | Cllr P Clark | Done
Note on G4: Resident email 2/10/17 Is there any way we could have some extra Christmas lights along the avenue to brighten up the dull winter and bring joy to many adults and children alike within the village? Every other local parish seems to push the boat out to bring some festive cheer.
Note on G5: Resident email 2/10/17 = I feel that we need a village defibrillator can you consider facilitating this for our village residents a potential lifesaving piece of equipment in an isolated location.
Note on D7: clerk: • Cinder Bank and especially around the school (A perennial problem area as cars always parked near school, during school hours – can you do before/after school?) • Waterside, where the school teachers park (Another perennial problem as school teachers park here, same as above) • All Parkside Drive (I realise there are few kerbs to sweep against, but please do your best as this is a central location with few footways) • All Monument Lane especially at the bottom around the Crossings Club and Railway House. • Elizabeth Park (I realise this is difficult due to cars being generally parked outside the terraced houses – have you a ‘’mini’’ sweeper?) • Nottingham Lane has lots leaf mulch near Oakes Row (if not already done from our recent previous emails)